## Project Planner
Victoria State Accident Data Set
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Data set analysis software development project
Planning tasks
Schedule WBS | 1 | 1 |  |  | 0%
Analysis Tasks
Define software requirements | 2 | 1 |  |  | 0%
Define required data | 3 | 1 |  |  | 0%
Define use case diagram | 4 | 1 |  |  | 0%
Design Tasks
Design GUI | 5 | 3 |  |  | 0%
Design Data Structure | 8 | 1 |  |  | 0%
Meeting with team staffs to evaluate | 9 | 1 |  |  | 0%
Build Tasks
Write code for displaying the all info about accidents | 10 | 2 |  |  | 0%
Write code for displaying the number of accidents in each hour | 12 | 2 |  |  | 0%
Write code for displaying accident type | 14 | 2 |  |  | 0%
Write code for displaying the impact of alcohol in accidnets | 16 | 2 |  |  | 0%
Write code for displaying the accident frquency in different locations | 18 | 2 |  |  | 0%
Test Tasks
Perform acceptance tests | 20 | 1 |  |  | 0%
Fix bugs | 21 | 2 |  |  | 0%
Schedule WBS
Define software requirements
Define required data
Define use case diagram
Design GUI
Design data structure
Meeting with staffs to evaluate
Write code for displaying the all info about accidents
Write code for displaying the number of accidents in each hour
Write code for displaying accident type
Write code for displaying the impact of alcohol in accidents
Write code for displaying the accident frequency in different locations
Perform acceptance tests
Fix bugs
Data set analysis software development project
Planning Tasks
Analysis Tasks
Design Tasks
Build Tasks
Test Tasks